## Slide 1
Local Government Engagement & Stakeholder Risks
SASSC Meeting, December 2024

## Slide 2: Stakeholder Management: Local Government Relations
Continuous proactive engagement with local government and communities, NGO’s and sector departments is prioritised
Good relatonships fostered with local and district municipalities
Emerging Risks/Issues
  Local Politics – decreased changes in political positions in recent past, but there is evidence of increasing hostility towards SARAO in Kareeberg and Hantam Local Municipalities with community sessions being used as political platforms
  Stakeholder Expectations – expection for contributions into projects outside mandate, as well as private sector scale CSIR investments such as those delivered by profit making entities (mining companies)

## Slide 3: Stakeholder Management: Local Economic Development
Excellent participation of local SMMEs and labour force in construction of SKA-MID and MeerKAT Extension
  Example - all transport service providers have been contracted by Power Adenco JV for SKA-MID infrastructre construction
  Appointment of Local Economic Development Officer will ensure greater attention on training and other skills development interventions
Emerging Risks/Issues
  Lack of local capacity (qualifying SMME’s and labour) – lack of capacity to meet needs of upcoming projects, which may result in the need to ‘bring in’ external contractors and labour – aggravates housing availability and potential anti-social behaviour
  Insufficient Healthcare – Healthcare facilities in Canarvon remain in dire condition, whilst response from provincial department of health has been slow

## Slide 4: Emerging, and Resolved, Risks and Issues
Land Use Applications
Project Name | Municipality | Application Status | Challenges / Comments
SKA-Mid Spiral Arms | Kareeberg, Karoo Hoogland & Hantam | Applications served at the applicable Tribunal meetings at end Nov ‘24. | Successfully unblocked by DSI, following refusal by Hantam Municipality to accept applications due to outstanding rates of land owners
Klerefontein Support Base Farm 527 | Kareeberg | Public consultation phase 29 November ‘24 to 28 Jan ‘25 | Initiation of public consultation significantly delayed by municipality, which now poses high risk to EOC construction schedule and delay penalties. Recommendation: DSI to be on alert to escalate should further delays be experienced in January
Loxton Repeater Station – Fibre Project ERF 61 | Ubuntu | Application 80% completed – await further information on water provision to be included in the application from Project Manager | Liaison & Communication with Ubuntu Municipality is challenging due to limited resources within the municipality. Recommendation: No intervention required

## Slide 5: Emerging, and Resolved, Risks and Issues
Development Approvals
Project Name | Municipality | Application Status | Challenges / Comments
Klerefontein Support Base Farm 527 | Kareeberg | Application and applicable documentation to be submitted by mid December ‘24 | Confirmation received from the District Municipality that the application for development approval and land use will be considered together in Feb ‘25. Recommendation: DSI to be on alert to escalate should further delays be experienced in January
Loxton Repeater Station – Fibre Project ERF 61 | Ubuntu | Site development plan is included in the land use application. Erf to be rezoning to a telecommunication facility. No infrastructure establishment as repeater equipment will be placed in specialised container | Recommendation: No intervention required

## Slide 6: Emerging, and Resolved, Risks and Issues
Municipal Rates & Taxes Gap in Kareeberg & Karoo Hoogland
  Negotiated outcome resulted in SARAO appointing land valuer to undertake supplementary valuation, and designate special use areas
  Action enables municipalities to levy rates & taxes against SARAO, albeit at reduced rates
  All efforts by SARAO undertaken to ensure a legal process for payment by SARAO of rates and taxes. However, to date since July 2023 Kareeberg Municipality has been unable to levy correct rates and taxes
    SARAO unable to pay irregular invoices
    Karoo Hoogland, and Hantam, have been able to invoice SARAO with the correct invoices, which have been subsequently paid