## Slide 1: Light Sources Update
Ian Martin
John Adams Institute Advisory Board Meeting
16th April 2026

## Slide 2: Contents
Ian Martin, Light Sources, JAI AB, 16/04/2026
Updates on Diamond-II Project
Project status (Procurement, Diamond Extension Building)
Kick-and-cancel injection scheme: prototyping and testing
Outline commissioning plan
Timeline
Updates from JAI members
Feasibility Studies of Incoherent Cherenkov Diffraction Radiation BPMs (A. Clapp, RHUL/DLS)
Optimising Injection at Diamond with Sample Efficient Bayesian Optimisation (S. Preston, UO/DLS/ALC)
Fast Beam Loss Monitor System for Diamond-II and Machine Learning Applications (C. Lehmann, UO/DLS)
Collective effects in Diamond-II (M Rakic, UO/DLS)
Conclusions

## Slide 3: Updates on Diamond-II Project
Ian Martin, Light Sources, JAI AB, 16/04/2026

## Slide 4: Project Status
Procurement for Diamond-II machine continues to progress:
Pre/main series sextupoles - 51 of 321 magnets delivered
4 of 52 storage ring girders have arrived
Pre-series DQ dipole delivered, DL dipole yokes / PM magnet blocks delivered to site and being assembled
All pre-series main vacuum vessels delivered, main series in production
5 of 6 Solid-State Amplifiers delivered (2 have passed SATs); 2 of 5 main EU-HOM-damped RF cavities due to be delivered in June; passive SC harmonic cavity due for delivery in September
Recent contracts placed: stripline kicker pulsers, thin septum magnets, booster kickers, fast corrector magnets, EBPM readout electronics, horizontal and vertical collimators, APPLE-II IDs
Tenders in-progress / imminent: PM/EM DC main septum, K18 3-pole wigger, K14 multipole wiggler
Main concerns regarding the schedule are delays to the storage ring quadrupole magnets and vacuum vessels - conversations on-going with suppliers for how to recover.
Ian Martin, Light Sources, JAI AB, 16/04/2026
Series sextupoles
Pre-series girders

## Slide 5: Diamond Extension Building
Hand-over completed Dec`25, occupied since Feb/Mar`26
Generally complete; some snagging items still to be resolved (delivery door heights, cranes in magnet lab, etc.)
Official opening on 4th March
Ian Martin, Light Sources, JAI AB, 16/04/2026
L-R: Gianluigi Botton (DLS CEO)
Sir Leszek Borysiewicz (Chair of DLS Board)
Roger Eccleston (STFC Exec Director)
Beamline assembly
Magnet lab
Vacuum vessel assembly
Vacuum vessel bakeout
Girder assembly
DEB2 Building

## Slide 6: Diamond Extension Building
Ian Martin, Light Sources, JAI AB, 16/04/2026
Magnet measurement bench
Vacuum assembly area
Kitchen / rest area
Office space
DEB2 storage area

## Slide 7: Kick-and-cancel injection scheme
Novel injection scheme planned for Diamond-II:
Enables transparent top-up injection
Minimises transverse wakefield effects and interaction with multi-bunch feedback allowing more charge to be accumulated
Upgrade path for future high-brightness lattices: can move to kick-and-aperture sharing injection
Key components
6 × short stripline kickers
±20 kV, 3 ns pulsers,
>2 kicks per 5 Hz injection cycle, tuneable delay
Septum magnet(s) with low leakage field:
  DC PM/EM main septum (7.4 degrees)
  Pulsed final thin septum (1.1 degrees)
Ian Martin, Light Sources, JAI AB, 16/04/2026
Straight I01
Straight K01
Turn = -3
Turn = 0
Injected bunch
Stored bunch
Kick from striplines
Septum plate
I01
K01
septum
striplines
magnets
Δμx ~ 90 deg

## Slide 8: Kick and cancel injection scheme
Prototype stripline kickers moved from Diamond transfer line to storage ring
Prototype 3 ns, ±20 kV pulser delivered by local company (Kentech Instruments)
Cabling / feed-throughs / attenuators chosen and tested
Finalising design of Diamond-II striplines
Ian Martin, Light Sources, JAI AB, 16/04/2026
3 ns
21 kV
1.5 µs
2 ns
<1 ns
>1 ns
<1 ns

## Slide 9: Kick and cancel injection scheme
Ian Martin, Light Sources, JAI AB, 16/04/2026
Cancellation after 5 turns
Anticipate further suppression:
adjust amplitude of 1st and 2nd kicks
compensate for tune-shift with amplitude
Pulse decay and reflections disturb 2 trailing bunches (cancelled after 3 turns)
    Single kick causes bunch to become unstable
  Amplitude of kick ~10-15% stronger than simple parallel-plate model prediction
time (min)
Current (mA)
    Double kick preserves full bunch charge
Impact on Stored Bunch
Impact on High-Charge Bunches
Impact on Trailing Bunches
Kick Calibration

## Slide 10: Commissioning Plan
Ian Martin, Light Sources, JAI AB, 16/04/2026
Phase | Months | Activities | Operations schedule
1 | Dec. ’28-Feb. ’29 | Machine commissioning & vacuum conditioning | 09:00-23:00 machine (6d/w) 23:00-09:00 + weekends vacuum conditioning
2 | Mar.-May ‘29 | Beamlines and machine commissioning, vacuum conditioning. | 09:00-16:00 beamlines 16:00-23:00 machine 23:00-09:00 + weekends vacuum conditioning
3 | Jun.-Sep. ‘29 | Regular beamline X-ray commissioning & first early Users | User mode: beamlines 6 days/week machine 1 day/week
4 | Oct.’29-Mar.’30 | 1st regular Allocation Period (AP46) | User mode: beamlines 6 days/week machine 1 day/week

## Slide 11: Commissioning Plan
Ian Martin, Light Sources, JAI AB, 16/04/2026
Parameter | Phase 2 | Phase 3 | Phase 4
Start date | 1/3/29 | 1/6/29 | 1/10/29
Machine Parameters |  |  | 
Beam current | ≥ 100 mA | 300 mA | 300 mA
Filling pattern | Commissioning | Standard | Standard + hybrid
Horizontal emittance | ≤ 250 pm | ≤ 160 pm | ≤ 160 pm
Vertical emittance | ≤ 20 pm | 8 pm | 8 pm
Operational Systems |  |  | 
Beam dump & collimators | ✓ | ✓ | ✓
Top-up | 4-kicker | Kick & Cancel | Kick & Cancel
IDs commissioned | ✓ | ✓ | ✓
Orbit feedback | FOFB (100 Hz) | FOFB (100 Hz) | FOFB (1 kHz)
Tune feedback | ✓ | ✓ | ✓
Multi-bunch feedback |  | ✓ | ✓
Emittance feedback |  | ✓ | ✓
Third harmonic cavity |  | ✓ | ✓

## Slide 12: Diamond-II Timeline
Ian Martin, Light Sources, JAI AB, 16/04/2026
Q1 | Q2 | Q3 | Q4
Mar 2023
2024/25 FY
Mar 2024
2025/26 FY
Mar 2025
2026/27 FY
Mar 2026
2027/28 FY
Mar 2027
Mar 2028
2028/29 FY
Mar 2029
2029/30 FY
Q1 | Q2 | Q3 | Q4
Q1 | Q2 | Q3 | Q4
Q1 | Q2 | Q3 | Q4
Q1 | Q2 | Q3 | Q4
Q1 | Q2 | Q3 | Q4
Q1 | Q2 | Q3 | Q4
July 2023 Approval for Diamond-II Project and start of funding
Dec 2025
Completion of the Diamond Extension Building ​
Dec 2027 ​
Start of the dark period ​​
Dec 2028 ​
Start of storage ring beam commissioning ​​​
Sep 2029 ​
First Phase of beamlines become operational
June 2029
End of the dark period; start of regular beamline X-ray commissioning
Jan 2030
First User on a Flagship Beamline
Mar 2030 ​​
End of the Diamond-II project ​
2023/24 FY
Aug 2026
Start of main girder assembly​
Jan 2028
Girder assembly complete​

## Slide 13: Updates from JAI Members
Ian Martin, Light Sources, JAI AB, 16/04/2026

## Slide 14: PhD Student: Alec Clapp (Viva Nov`25, Completed Mar`26)
Ian Martin, Light Sources, JAI AB, 16/04/2026
“Feasibility study on the use of incoherent Cherenkov Diffraction Radiation to develop a non-invasive BPM”
Supervisors: P. Karataev and L. Bobb
Image participants (left to right): Pavel Karataev, Alec Clapp, Thibaut Lefevre (CERN, External examiner), Matthew Wing (UCL, Internal Examiner).
https://www.royalholloway.ac.uk/research-and-education/departments-and-schools/physics/news-physics/2025-11-13-congratulations-to-dr-alec-clapp/
A. Clapp et al., Proc. of IBIC’2024, Beijing, China, TUP33
Demonstration of a 1D, dual pick-up ChDR BPM using pick-ups at visible wavelengths
Electron beam passes between two quartz targets
ChDR is emitted by target and collected by collimators
Light propagates though fibre optic feedthroughs to PMT

## Slide 15: DPhil Student: Shaun Preston (started 2023)
Main topic of study is to develop a Gaussian Process Optimiser (GPO), targeting online tasks (sample efficiency for sequential measurements key!)
Topics investigated:
Kernel composition (behaviour of system being modelled)
Acquisition function (where to sample next)
Pre-conditioning with random sampling / known ‘good’ solutions
Training neural network on model to use as a ‘prior’ for optimisation
Use of variational auto-encoders to reduce degrees of freedom
Guiding the optimisation: weighting with charge, position limits on BPMs
Progress over the last 12 months:
Maximise LTB and BTS transfer efficiency
Different variables: H/V steerers, pulsed magnets, quadrupoles
Developed an interactive tool for control room optimisation tasks
Ian Martin, Light Sources, JAI AB, 16/04/2026
“Optimising Injection at Diamond Light Source with Sample Efficient Bayesian Optimisation”
Supervisors: P. Burrows and I. Martin
Interactive GUI
Starting values (25%)
Initial sampling
Optimisation (45%)
10 minutes
BR Inj. Eff. (%)

## Slide 16: DPhil Student: Corey Lehmann (started 2023)
Ian Martin, Light Sources, JAI AB, 16/04/2026
Supervisors: P. Burrows and L. Bobb
“Fast Beam Loss Monitor System for Diamond-II and Machine Learning Applications”
C. Lehmann, et al., Proc. IBIC 2025, Liverpool, UK, Sep. 2025, pp. 58-61. doi:10.18429/JACoW-IBIC2025-MOPCO04
Fast BLMs have been calibrated and installed in the Diamond storage ring
Neural network models developed to match losses against known ID states
Example of a 24-hour period of Test data for the Collimator BLD
Red shaded areas indicate where anomalies are detected from the measured and predicted data being sufficiently diverged.
true measured values
values predicted by a 1x32 NN model

## Slide 17: Joint JAI/DLS PDRA: Milica Rakic (starts May(?) 2026)
Ian Martin, Light Sources, JAI AB, 16/04/2026
Supervisors: P. Burrows and I. Martin
Diamond Multi-bunch feedback
“Collective Effects Studies for Diamond-II”
Simulated horizontal coupled-bunch growth rates for Diamond-II
striplines
collimators
Resistive wall
Diamond-II studies:
Update single and multi-bunch threshold estimates with latest impedance database and vacuum pressure profile
Collective effects / multi-bunch feedback impact on kick-and-cancel injection
New topics: impact of space charge and IBS, optics errors
Diamond machine development:
Characterisation and optimisation of existing multi-bunch feedbacks
Cross-checking / validation of Diamond-II studies
Long-term monitoring of instability thresholds / machine impedance / IDs
General simulation updates:
Implementation of collective effects in PyAT, adoption of Xsuite
Comparison of particle tracking results with Vlasov-solvers

## Slide 18: Conclusions
JAI continues to be active in many areas of light source design and operation:
Enhanced performance / special operating modes / facility design
Photon / electron beam diagnostics
Exploitation of machine learning and related techniques
Directly supports and well-integrated with Diamond-II Project.
Collaborations / synergies with ISIS, ILC and Ada Lovelace Centre
Providing training and expertise in light sources for next generation of accelerator physicists:
Three PhD/DPhil Studentships (RHUL and Oxford)
Joint Diamond / JAI PDRA working on Diamond-II
Ian Martin, Light Sources, JAI AB, 16/04/2026