## Slide 1: Following up the FTEC program
FTEC 2015 – Workshop II
April 2016

## Slide 2: Objetives
To improve the employability of FTEC trainees.
To promote access to professionals trained in CERN technologies by Spanish companies.
To provide information to FTEC trainees about the catalogue of Spanish companies.
To create a long term network of contacts between technicians and companies, to facilitate new collaborations and opportunities.

## Slide 3: Planned actions:
First contact
4Q 2016
Event in CDTI (Madrid)
4Q 2016
Employment network
1Q 2017

## Slide 4: First contact:
A first contact after this summer (4Q 2016):
  We will send an e-mail to the trainees, with the list of companies with activities in CERN.
  The trainees may show interest in some companies, and depending on the response, some ad hoc contacts will be planned (taking advantage of regular visits to CERN by the companies).

## Slide 5: Event in CDTI:
CDTI is planning an event in Madrid to spread CERN opportunities within Spanish industry (4Q 2016).
All trainees will be invited to attend, where they will meet all the companies.
A general presentation of the FTEC program will be performed, explaining the kind of projects undertaken.
A leaflet will be provide to the companies, with general information about FTEC program, the technical areas involved, and a link to a website with more detail.

## Slide 6: Employment Network:
We are studying several possibilities.
The idea is to capitalise digital tools already working (e.g. LinkedIn), to facilitate the creation of the long term network of contacts.
A platform reusable in next FTEC calls, to develop a big database of professionals in the long-term.
Accessible to the companies: A tool to search professionals trained in specific technologies.