## Slide 1
Anders Wallander
Head of Controls Division
ITER Organization Central Team
ITER Status
Anders Wallander Controls Division ITER Organization

## Slide 2: Quick reminder what ITER is about
Demonstrate technical feasibility of nuclear fusion as energy source
Lawson criterion: Temperature * Density * Time > Big Number
ITER is an international project based on in-kind contributions

## Slide 3: The ITER Tokamak
An intense magnetic field, generated by powerful superconducting magnets, shapes, heats and confines the hot plasma, and keeps it away from the vacuum vessel wall.
Vacuum Vessel: 8 000 t. 850 m3
18 TF Coils: 360 t. 17-m high
1 Central Solenoid: 1 000 t. 13-m high
6 PF Coils: 200-400 t. 8 to 24 m diameter
Cryostat: 30 x 30 m
About 50 % of these components have been delivered on site

## Slide 4
December 2021

## Slide 5
January 2022

## Slide 6
February 2022

## Slide 7
May 2022

## Slide 8
The “Big Lift” May 11, 2022
First out of nine subsectors lifted and installed in the Tokamak Pit
A subsector consists of one 40o vacuum vessel sector with thermal shield and two toroidal field coils weighting 1200 tons
3D real-time display

## Slide 9
ITER Control System Architecture

## Slide 17
Reactive Power Compensation is the first plant system using fast control (kHz) and high performance networks
Low voltage commissioning is almost complete
This is first part of the magnet power supplies

## Slide 18
  Magnet Power Supplies
  Electron cyclotron heating
  Vacuum
  Structures
  Magnets
  Fueling
  Diagnostics
Coming up…

## Slide 19
13% of first plasma integration scope complete
Today
Metrics (hardware)
Time

## Slide 20
20% of first plasma integration scope complete
Today
Metrics (software)
Time

## Slide 21
  Integration of in-kind contributions is challenging as expected (but actually worse than we thought)
  Delivered hardware and software is late and of poor quality (with exception of course)
  We need to do a lot of rework to be able to integrate
  Lately, we are doing more and more (software) scope transfer, meaning we take over the responsibility for (sometimes) design, manufacturing and testing (at a cost)
  This is technically a good solution, but we must balance available resources and total scope
Integration Lessons Learned

## Slide 22
Control Building construction
  Control building construction almost complete and installation of servers and networks starting next month
  Main Control room start of operation in 2024
  Final configuration of control room will have 80 seats

## Slide 23
Network Infrastructure construction
174 cubicles
159 connection panels
812 cables
2515 client connections

## Slide 24
Operation (High-level) Applications
Pulse Schedule Preparation System (PSPS)
  Define parameters, lifecycle management, workflow
Supervisory System (SUP)
  Global states, integration, sequencer, configuration
Plasma Control System (PCS)
  Real-time control of plasma during pulsing
Data Handling (DA)
  Acquire, archive, store and give access
Remote Participation (RP)
  Data transmission, networking to remote sites, virtual collaboration tools
Bob Gunion Wed 12:10 – ITER Operation Applications: Status and Future Development
Leonid Lobes Thu 09:35 – Study on EPICS Communication over Long Distance
Anze Zagar Thu 12:25 – EPICS (pvAccess) Transport Layer for the ITER Real-Time Framework (RTF)

## Slide 25
Plant Systems
CODAC incl. Plasma Control System
Interlocks
Safety
Control & Monitoring
Interlock
Functions
Safety
Functions
OPERATION
PROTECTION
Defence in depth

## Slide 26
Summary
ITER control system is in construction, commissioning and operation
Integration of in-kind contributions is 15 % complete towards first plasma
Mitigation actions to ease integration are continuously being explored
Final infrastructure construction, with networks, servers and control room, starts now
More and more effort is put in the development of high level operation applications in close collaboration with science and operation

## Slide 27
We are always looking for people to join our team to meet the challenges and reap the rewards in the coming years
https://www.iter.org/jobs