## Slide 1: Accelerator Comms Project
IUPAP WG 14
A/Prof. Suzie Sheehy, University of Melbourne
suzie.Sheehy@unimelb.edu.au

## Slide 2: Deliverables
Creative Commons licensed Presentation materials (PPTX) created in a consistent, attractive style, to include:
  1) a 5-slide ‘intro to accelerators’ deck (audience: policy makers, other fields of expertise, and general public audiences)
  2) a 10-slide deck for each of the ‘key messages’ (audience:
  3) a 50-minute ‘keynote talk’ presentation covering all key messages
Each presentation will come with notes and dot points to include when presenting the materials, colour coded with points that a presenter may wish to deliver to different audiences (e.g. high school students, general public, professionals/policy makers)
A brief report including relevant evaluation and lessons-learned from the project, to potentially be published somewhere suitable e.g. at IPAC or in a Physics Education journal.

## Slide 3: Audiences:
Those who may DELIVER the materials include professionals, PhD students, teachers and outreach teams who engage with particle accelerators in some way.
The audiences REACHED by the materials will include: high school students, science and non-science University students, researchers in fields adjacent to or who make use of accelerators, policy makers etc.

## Slide 4: Timeline
Pre-project:
  Define the project
  Agreement signed
  Invoicing – (this week)
  Casual recruitment in process
Month 1:
  Onboarding [imminent!]
  Briefly collect (or use from other project) existing materials relevant to project - ongoing
  Refine ‘key ideas’ and map out each presentation.
    Identify key ideas [see later] and flow of ‘stories’ to include
  Create ‘style’ templates for PPTX and identify artist for graphics
Month 2 and 3:
  Feedback on ‘style’ of presentation materials
  Feedback on content map from IUPAP-WG
     Seek input on detailed content from content map from WG members.
  Begin drafts of all presentations and accompanying notes
  Curate a distribution list to disseminate materials to, with help of IUPAP-WG
  Create an evaluation plan to assess project success (metrics, evaluation questionnaire, etc…)

## Slide 5: Timeline (cont…)
Month 4:
  Finalise presentations and finalise accompanying notes.
  Distribute to IUPAP-WG members for comment/feedback/trial run [ need volunteers! ]
Month 5:
  Amend according to feedback, finalise all materials
  Integrate materials into website (to be decided which one…? IUPAP WG-14 site?)
  Disseminate to mailing list
  Track hits/downloads/etc
Month 6:
  ‘Publish’ project and materials along with accompanying notes (Physics Education journal? PRAB? Other?)
  Contingency time for website integration/evaluation.

## Slide 6: Pre-Project Decisions to be made:
What are the three-five (3-5) “key messages” or “big ideas” that the IUPAP WG-14 would like to include as the themes to be addressed?
  Suggestions so far include (for example):
    Our future depends on particle accelerators (sustainability focus, including environmental and societal spin-offs, UN SDGs etc)
    Particle beams are a force for good: impact in health and medicine
    Accelerators are the hidden enablers: from discovery to industry
    Future particle accelerators rely on fundamental breakthroughs in a wide range of areas: electromagnetism, plasma physics, beam dynamics, lasers, materials etc
    ? Human force of collaboration?
(translation: include and re-upload?), follow-up/contact points
CC: acknowledge original source (disclaimer?)
Small working group of sub-committee members for oversight: volunteers?
A/Prof. Suzie Sheehy, University of Melbourne
suzie.Sheehy@unimelb.edu.au